## Assumptions
Harborline Mutual — TCO, FinOps and Value Assumptions (ILLUSTRATIVE)
Legend: blue = input you can change · black = formula · green = link to another sheet · yellow fill = quote-based or key assumption to replace. Year 1 = Oct 2026–Sep 2027 (M1–M12).
Timeline drivers (from docs/migration-roadmap.md)
Driver | Y1 | Y2 | Y3 | Y4 | Y5 | Basis
Teradata months at current contract rate | 9 | 0 | 0 | 0 | 0 | Oct 2026 – Jun 2027: term ends 30 Jun 2027 (M9)
Teradata months on the one-year bridge (+25%) | 3 | 9 | 0 | 0 | 0 | ADR-028: bridge Jul 2027 – Jun 2028. Paid to term end even though switch-off is May 2028 (M20)
Informatica PowerCenter months licensed | 12 | 8 | 0 | 0 | 0 | Switched off with Teradata in May 2028 (M20). Assumes co-termination is negotiable (yellow input below)
SAS licence share still paid | 100% | 75% | 0% | 0% | 0% | Phase 8: desktop seats step down as programs port from M9; grid kept until reserving ports; retired M24
Data-center hosting share still paid | 100% | 70% | 0% | 0% | 0% | Falls away with the appliance (M20) and the SAS grid (M24)
Status quo: appliance refresh (1 = in this year) | 1 | 0 | 0 | 0 | 0 | current-state.md §6: ~$6.0M one-time refresh if Teradata is renewed
GCP data platform live (share of steady-state run) | 40% | 90% | 100% | 100% | 100% | Phase 0 foundation + claims domain in Y1; policy, reserving, regulatory in Y2
Dual-run migration reservation (avg slots) | 300 | 300 | 0 | 0 | 0 | ADR-030: dedicated migration reservation while domains dual-run (to M18)
Assistant average active users | 808 | 4358 | 4400 | 4400 | 4400 | Pilot 300 (Mar–May 2027) + scale ramp Jun–Sep → 9,700 user-months in Y1; full 4,400 from Nov 2027
Assistant fixed infrastructure share | 50% | 100% | 100% | 100% | 100% | Pilot-scope hot tier and gateway from M3–M6; full sizing from Y2
Assistant run-team share | 75% | 100% | 100% | 100% | 100% | Team stands up at M3 (Phase 1)
Search-time reduction achieved (claims staff) | 15% | 25% | 25% | 25% | 25% | ASSUMPTION — no target is stated in requirements.md; A2 measures it in the pilot
Legacy estate (current-state.md §6)
Input | Value | Unit |  |  |  | Basis / source
Teradata licence and support | 3900000 | $ / yr |  |  |  | current-state.md
Bridge-extension uplift | 25% | % |  |  |  | requirements.md: one-year bridge at +25%
Extended hardware support for the ageing appliance | 250000 | $ / bridge-yr |  |  |  | ILLUSTRATIVE — ADR-028 negotiating term; quote-based
SAS licences (grid + desktop) | 1400000 | $ / yr |  |  |  | current-state.md
Informatica PowerCenter licence and support | 900000 | $ / yr |  |  |  | current-state.md. Month-by-month exit assumes co-termination — confirm contract
Data-center hosting share | 600000 | $ / yr |  |  |  | current-state.md
Teradata appliance refresh (status quo only) | 6000000 | $ one-time |  |  |  | current-state.md
Legacy data-platform run baseline (NFR-11) |  | $ / yr |  |  |  | Sum of the four recurring lines = $6.8M
GCP data platform — steady state (gcp-implementation.md, ADR-021/026)
Input | Value | Unit |  |  |  | Basis / source
BigQuery Enterprise baseline reservation (ELT, BI, data science) | 1200 | slots |  |  |  | ILLUSTRATIVE sizing; reservations per workload project (ADR-026)
BigQuery Enterprise, 1-year commitment | 0.054 | $ / slot-hr |  |  |  | Google list price, US, Sept 2026
BigQuery Enterprise Plus reservation (reserving, regulatory; managed DR) | 300 | slots |  |  |  | ILLUSTRATIVE; Enterprise Plus for managed disaster recovery (NFR-9)
BigQuery Enterprise Plus, 1-year commitment | 0.09 | $ / slot-hr |  |  |  | Google list price, US, Sept 2026
Autoscale slots above baselines (average) | 400 | slots |  |  |  | ILLUSTRATIVE — close-week and month-end peaks
BigQuery Enterprise, pay-as-you-go (autoscale) | 0.06 | $ / slot-hr |  |  |  | Google list price, US, Sept 2026
BI Engine reservation for Tableau | 100 | GiB |  |  |  | ILLUSTRATIVE
BI Engine price | 0.0416 | $ / GiB-hr |  |  |  | ILLUSTRATIVE list-price basis
Raw data estate today | 450 | TB |  |  |  | NFR-10
Data growth | 20% | % / yr |  |  |  | NFR-10
Billable storage per raw TB (compression vs. bronze/silver/gold + time travel) | 0.8 | × |  |  |  | ASSUMPTION: ~3:1 compression offset by three layers
Cloud Storage Standard (Iceberg data files) | 0.023 | $ / GB-month |  |  |  | ILLUSTRATIVE list-price basis; Iceberg-managed tables store data in Cloud Storage
Datastream CDC volume (Guidewire Oracle) | 2000 | GB / month |  |  |  | ILLUSTRATIVE
Datastream CDC price | 2 | $ / GB |  |  |  | ILLUSTRATIVE list-price basis (first volume tier)
Dataflow (batch files, vendor feeds, document chunker) | 60000 | $ / yr |  |  |  | ILLUSTRATIVE
Colab Enterprise / serverless Spark (actuarial, data science) | 90000 | $ / yr |  |  |  | ILLUSTRATIVE — replaces SAS compute
Dataplex Universal Catalog + lineage | 40000 | $ / yr |  |  |  | ILLUSTRATIVE
Sensitive Data Protection discovery | 45000 | $ / yr |  |  |  | ILLUSTRATIVE
Dedicated Interconnect (redundant ports, cross-connects, carrier) | 120000 | $ / yr |  |  |  | ILLUSTRATIVE — ADR-026
Cloud Logging / Monitoring | 60000 | $ / yr |  |  |  | ILLUSTRATIVE
Security Command Center, KMS/CMEK, Cloud Armor | 90000 | $ / yr |  |  |  | ILLUSTRATIVE
Archive + regulatory export buckets | 10000 | $ / yr |  |  |  | ILLUSTRATIVE
Google Cloud support | 4% | % of platform spend |  |  |  | ILLUSTRATIVE — premium-class support
Dual-run reservation price (pay-as-you-go) | 0.06 | $ / slot-hr |  |  |  | Enterprise PAYG: temporary, no commitment
FinOps analyst, loaded (ADR-008) | 170000 | $ / yr |  |  |  | ILLUSTRATIVE — new role, hired in Phase 0
Claims assistant — per-query drivers (ADR-006, ADR-008, ADR-024)
Input | Value | Unit |  |  |  | Basis / source
Assistant population at scale | 4400 | users |  |  |  | NFR-10: ~3,800 claims + ~600 underwriting
of which claims staff | 3800 | users |  |  |  | ADR-029
Queries per user per business day | 25 | queries |  |  |  | NFR-10: ~110K/day ÷ 4,400
Business days per year | 250 | days |  |  |  | Assumption
Input tokens per query (retrieved context + claim + system) | 6000 | tokens |  |  |  | ADR-008 decomposition
Output tokens per query | 500 | tokens |  |  |  | ADR-008 decomposition
Share routed to the fast model | 70% | % |  |  |  | ADR-008 lever: small model for lookups, frontier for summaries
Fast model input price | 0.3 | $ / M tokens |  |  |  | ILLUSTRATIVE Flash-class price; confirm on Vertex AI
Fast model output price | 2.5 | $ / M tokens |  |  |  | ILLUSTRATIVE Flash-class price
Frontier model input price | 3 | $ / M tokens |  |  |  | ILLUSTRATIVE Sonnet-class price; confirm US multi-region pricing
Frontier model output price | 15 | $ / M tokens |  |  |  | ILLUSTRATIVE Sonnet-class price
Reranking (Vertex ranking) | 1 | $ / 1,000 queries |  |  |  | ILLUSTRATIVE
Model Armor screening | 0.1 | $ / M tokens |  |  |  | ILLUSTRATIVE
Online evaluation sample scored by a second model | 5% | % of queries |  |  |  | ADR-007: different scorer model
Audit + logging per query | 0.0002 | $ / query |  |  |  | ILLUSTRATIVE — ~30 KB per interaction
Vertex AI Vector Search serving (hot + reference, 2 regions) | 150000 | $ / yr |  |  |  | ILLUSTRATIVE sizing (ADR-023)
New claim documents per day | 25000 | docs |  |  |  | NFR-10
Pages per document | 4 | pages |  |  |  | Assumption
Document AI OCR price | 1.5 | $ / 1,000 pages |  |  |  | ILLUSTRATIVE list-price basis
Embeddings (new documents + re-embeds) | 10000 | $ / yr |  |  |  | ILLUSTRATIVE
Warm tier: BigQuery search index + queries | 40000 | $ / yr |  |  |  | ILLUSTRATIVE (ADR-023)
Apigee subscription (AI gateway) | 180000 | $ / yr |  |  |  | ILLUSTRATIVE — quote-based (ADR-024)
Cloud Run (assistant + retrieval service) | 50000 | $ / yr |  |  |  | ILLUSTRATIVE
Evaluation harness runs + red-team suite | 40000 | $ / yr |  |  |  | ILLUSTRATIVE (ADR-007)
Audit store (Bucket Lock + BigQuery copy) | 15000 | $ / yr |  |  |  | ILLUSTRATIVE — 7-year retention (NFR-6)
Assistant run team (product owner, 2 engineers, golden-set SME share) | 600000 | $ / yr |  |  |  | ILLUSTRATIVE loaded cost; outside NFR-11's unit-cost definition
Pilot users (A2 is measured here) | 300 | users |  |  |  | ADR-029
Assistant value (capacity released)
Input | Value | Unit |  |  |  | Basis / source
Loaded cost per claims FTE | 95000 | $ / yr |  |  |  | ILLUSTRATIVE — quote from HR/Finance
Share of adjuster time spent searching | 30% | % |  |  |  | problem-statement.md (adjusters report ~30%)
Share of released capacity that becomes financial value | 50% | % |  |  |  | ASSUMPTION: avoided hiring, overtime and independent-adjuster spend; the rest is quality
NFR-11 ceilings and decision robustness
Input | Value | Unit |  |  |  | Basis / source
Assistant unit-cost ceiling (all-in) | 0.05 | $ / query |  |  |  | NFR-11
Proposed pilot gate on variable cost per query | 0.02 | $ / query |  |  |  | Step 12 amendment to gate A2 (ADR-029)
GCP weighted score (Step 9) | 3.9 | / 5 |  |  |  | decision-matrix.md
Azure weighted score (Step 9) | 3.675 | / 5 |  |  |  | decision-matrix.md (runner-up)
Cost criterion weight | 15% | % |  |  |  | decision-matrix.md

## PlatformRunRate
GCP Data Platform — Steady-State Run-Rate (annual, illustrative)
Like-for-like with the $6.8M legacy baseline: licences, infrastructure and support only. People, Tableau and Guidewire are outside both.
Line item | Annual $ | Formula basis
BigQuery Enterprise baseline reservation |  | slots × $/slot-hr × 8,760
BigQuery Enterprise Plus reservation |  | slots × $/slot-hr × 8,760
BigQuery autoscale slots |  | avg slots × $/slot-hr × 8,760
BI Engine |  | GiB × $/GiB-hr × 8,760
Datastream CDC |  | GB/month × $/GB × 12
Dataflow |  | input
Colab Enterprise / serverless Spark |  | input
Dataplex Universal Catalog + lineage |  | input
Sensitive Data Protection |  | input
Dedicated Interconnect |  | input
Logging / Monitoring |  | input
Security services |  | input
Archive + export buckets |  | input
Subtotal — services (before support)
Google Cloud support on services |  | subtotal × support %
Services incl. support (does not grow with data)
Storage at today's volume, incl. support |  | raw TB × billable factor × 1,000 × $/GB-mo × 12 × (1 + support); grows with data in FiveYearTCO
Steady-state platform run-rate at today's volume
Share of the $6.8M legacy baseline

## AssistantUnitCost
Claims Assistant — Unit Cost per Query (illustrative)
NFR-11 defines 'all-in' as retrieval + inference + logging. The run team is shown separately as 'fully loaded'.
Line item | Value | Formula basis
Variable cost per query
Fast-model generation |  | (in × $in + out × $out) ÷ 1M
Frontier-model generation |  | (in × $in + out × $out) ÷ 1M
Routed generation |  | fast share × fast + rest × frontier
Reranking |  | $/1,000 ÷ 1,000
Model Armor screening |  | tokens × $/M ÷ 1M
Online evaluation sampling |  | sample % × frontier cost
Audit + logging |  | input
Variable cost per query |  | sum
Fixed AI infrastructure (annual, at scale)
Vector Search serving |  | input
Document AI OCR (new documents) |  | docs/day × pages × 365 × $/1,000 pages
Embeddings |  | input
Warm tier (BigQuery search) |  | input
Apigee |  | input
Cloud Run |  | input
Evaluation harness + red team |  | input
Audit store |  | input
Fixed AI infrastructure |  | sum
Unit cost at full scale
Queries per year at full scale |  | users × queries/day × days
Fixed infrastructure per query |  | fixed ÷ queries
All-in unit cost per query (NFR-11 definition) |  | variable + fixed share
Run team per query |  | team ÷ queries
Fully loaded cost per query (incl. run team) |  | all-in + team

## OneTime
One-Time Program Costs and Phasing (illustrative)
Blue = inputs. Track: Data = Teradata/SAS exit and platform; AI = claims assistant. Phasing % must sum to 100% (column R).
Item | Track | Quantity | Unit cost ($) | Unit | Total ($) | Y1 % | Y2 % | Y3 % | Y4 % | Y5 % | Y1 $ | Y2 $ | Y3 $ | Y4 $ | Y5 $ | Basis | Phasing check
Gate G0 proofs of concept (Iceberg parity, translation, model terms) | Data | 1 | 300000 | lump sum |  | 100% | 0% | 0% | 0% | 0% | [5 empty] | ADR-027 gate G0, M1–M3
Landing zone, VPC-SC, WIF⇄Entra, Dataplex, Apigee setup (partner) | Data | 1 | 450000 | lump sum |  | 100% | 0% | 0% | 0% | 0% | [5 empty] | Phase 0
Historical bulk load (Transfer Appliance, Data Transfer Service) | Data | 1 | 80000 | lump sum |  | 100% | 0% | 0% | 0% | 0% | [5 empty] | ADR-025/026
Automated translation runs + test harness | Data | 1 | 250000 | lump sum |  | 70% | 30% | 0% | 0% | 0% | [5 empty] | BigQuery translator (SQL, BTEQ, TPT)
Manual rewrite of untranslated objects (1,800 × 30%) | Data | 540 | 3500 | per object |  | 45% | 55% | 0% | 0% | 0% | [5 empty] | 25–35% midpoint; G0 check 3 resizes this
Informatica job re-engineering to Dataform (2,400 × 60% retained) | Data | 1440 | 1800 | per job |  | 40% | 60% | 0% | 0% | 0% | [5 empty] | Rationalization retires ~40% of jobs
Unified silver model (party/policy/claim, survivorship, crosswalks) | Data | 1 | 900000 | lump sum |  | 60% | 40% | 0% | 0% | 0% | [5 empty] | ADR-001, logical-design.md
Domain reconciliation + dual-run effort | Data | 5 | 250000 | per domain |  | 40% | 60% | 0% | 0% | 0% | [5 empty] | ADR-030: claims, policy/billing, reserving, regulatory, remaining
Coastal ingestion + 2024 Snowflake account close-out | Data | 1 | 200000 | lump sum |  | 100% | 0% | 0% | 0% | 0% | [5 empty] | Phases 0 and 5
Tableau repointing of retained reports | Data | 1 | 350000 | lump sum |  | 50% | 50% | 0% | 0% | 0% | [5 empty] | ~30% of reports retained
SAS program porting to Python/SQL (900 × ~65% retained) | Data | 600 | 2500 | per program |  | 25% | 75% | 0% | 0% | 0% | [5 empty] | Phase 8, M9–M24
Decommission + final archive (Teradata, Informatica) | Data | 1 | 200000 | lump sum |  | 0% | 100% | 0% | 0% | 0% | [5 empty] | M19–M20, gate T
Program management + change (data track) | Data | 1 | 1000000 | lump sum |  | 50% | 50% | 0% | 0% | 0% | [5 empty] | Illustrative
Assistant build (6 engineers × 6 months) | AI | 36 | 15000 | per eng-month |  | 100% | 0% | 0% | 0% | 0% | [5 empty] | Phase 1, M3–M6 + pilot hardening
Golden set + red-team suite (Claims SMEs, red team) | AI | 1 | 250000 | lump sum |  | 100% | 0% | 0% | 0% | 0% | [5 empty] | ADR-007, ~1,500 questions
Initial document indexing (hot + reference tiers, OCR, embeddings) | AI | 1 | 200000 | lump sum |  | 60% | 40% | 0% | 0% | 0% | [5 empty] | ADR-006; Coastal from M12
Training and adoption (4,400 users) | AI | 1 | 350000 | lump sum |  | 50% | 50% | 0% | 0% | 0% | [5 empty] | ADR-029 scale phase
Total one-time — Data track
Total one-time — AI track
Total one-time

## FiveYearTCO
Five-Year Cost and Value — GCP Target vs. Status Quo (illustrative)
All figures in $ unless stated. Year 1 = Oct 2026–Sep 2027. Green = links to other sheets.
Line | Y1 | Y2 | Y3 | Y4 | Y5 | 5-yr total | Formula basis
A1. Data platform — STATUS QUO (renew Teradata, refresh appliance, keep SAS + Informatica)
Teradata licence and support | [6 empty] | Flat — conservative (no renewal uplift)
Appliance refresh | [6 empty] | current-state.md §6
SAS | [6 empty] | Flat
Informatica | [6 empty] | Flat
Data-center hosting | [6 empty] | Flat
STATUS QUO TOTAL
A2. Data platform — TARGET (GCP-native, per the Step 11 roadmap)
Teradata at current rate | [6 empty] | $/yr ÷ 12 × months
Teradata bridge (+25%) | [6 empty] | ADR-028
Teradata extended hardware support | [6 empty] | ADR-028 negotiating term
Informatica (until M20) | [6 empty] | $/yr ÷ 12 × months
SAS (step-down to M24) | [6 empty] | $/yr × share
Data-center hosting | [6 empty] | $/yr × share
GCP platform services incl. support | [6 empty] | PlatformRunRate × share live
GCP storage (grows 20%/yr) | [6 empty] | Today's storage × share live × growth
Dual-run migration reservation | [6 empty] | ADR-030 avg slots × PAYG × 8,760
FinOps analyst | [6 empty] | ADR-008 (people; outside the NFR-11 test)
One-time program — Data track | [6 empty] | OneTime sheet
TARGET TOTAL
DATA PLATFORM SAVING (status quo − target)
Cumulative
B. Claims assistant — cost and value (NFR-11: must justify itself on unit economics)
Assistant queries (count) | [6 empty] | avg users × queries/day × days
Variable (inference, rerank, screening, eval, logging) | [6 empty] | queries × variable $/query
Fixed AI infrastructure | [6 empty] | AssistantUnitCost × share
Assistant run team | [6 empty] | input × share
One-time program — AI track | [6 empty] | OneTime sheet
ASSISTANT COST
Value: claims capacity released | [6 empty] | claims users × $/FTE × 30% searching × reduction × realization
ASSISTANT NET (value − cost)
Cumulative
All-in unit cost per query (infra only, NFR-11 definition) | [6 empty] | Above the $0.05 ceiling in Y1 by construction: fixed costs over pilot volumes
C. Program overall (A + B)
Total benefit (data-platform saving + assistant value)
Total assistant cost
PROGRAM NET
Cumulative
Summary metrics
Steady-state data-platform run-rate, Y3 (GCP services + storage)
as a share of the $6.8M baseline
Steady-state data-platform saving, Y3
Data-platform payback year
Bridge-year Teradata payment (licence + hardware support)
Assistant steady-state value ÷ steady-state cost (Y3)
Program payback year (A + B)

## NFR11Tests
NFR-11 Tests, Gate A2 Check and Decision Robustness
Test | Value | Result | Basis
1. Data-platform run-rate ≤ $6.8M legacy baseline (excluding the AI capability)
Legacy baseline |  |  | current-state.md §6
GCP steady-state run-rate (Y3) |  |  | FiveYearTCO summary
Headroom below baseline
Extra average BigQuery slots before the baseline is breached |  |  | headroom ÷ (PAYG $/slot-hr × 8,760 × (1 + support))
Run-rate multiple that would breach the baseline |  |  | baseline ÷ run-rate
2. Assistant unit cost ≤ $0.05 per query (all-in = retrieval + inference + logging)
Variable cost per query |  |  | AssistantUnitCost
All-in unit cost at full scale |  |  | AssistantUnitCost
Break-even queries per year for the ceiling |  |  | fixed ÷ (ceiling − variable)
Break-even active users |  |  | queries ÷ (queries/day × days)
as a share of the 4,400-user population
Fully loaded unit cost incl. run team |  |  | Outside NFR-11's definition; shown for honesty
3. Gate A2 as written in ADR-029 (cost per query ≤ $0.05, measured in the pilot)
Pilot queries per year (300 users)
All-in unit cost during the pilot |  |  | variable + pilot-sized fixed ÷ pilot queries
Amended A2: variable cost per query ≤ $0.02 (measured) |  |  | Step 12 amendment (ADR-029 addendum)
Amended A2: modeled all-in at scale ≤ $0.05 (from measured tokens)
4. Assistant value robustness
Break-even search-time reduction (steady state) |  |  | Y3 assistant cost ÷ (claims FTE × $ × 30% × realization)
as a share of an adjuster's working day
5. Can cost evidence alone flip ADR-027?
GCP lead over Azure (weighted) |  |  | decision-matrix.md
GCP cost-score drop needed to lose the lead |  |  | lead ÷ cost weight; GCP scored 3.5 on cost